## Лист2
Terms of Reference
to Agreement №____________
Name of the Expert: ______________
Position name |  | Short-term Technical expert on Needs Assessment of the USAID "Smart Waters" Project in Afghanistan
Project code: С 1069 USAID "Smart Waters"
Budget line 3.1 Regional Expert works
Focus of the Assessment need to be done on knowledge in water resources management (re-training of government officials), academis&research cooperation and basin approaches.
№ | Services | Amount of working days | Payment for one day (GROSS, USD) | Total Sum (amount of working days х rate per day) | Deliverables
1 | Development of the vision and approach on implementation of the Needs Assessment in Afghanistan based on the regional approach and methodology (attached). Agreement of the vision and approach with CAREC and USAID. |  |  |  | Presentation on implementation of the Needs Assessment approved by CAREC and USAID
2 | Organization of the national consultations with key project parters in Afghanistan (MEW, NEPA, MoHE, others) for presentation of the goals, objectives of the assessment as well as with detailed presentation of the agreed approach and methodology. |  |  |  | National consultations held, working contacts with main national partners of the project established. Presented approach well received and agreed. Schedule for interviewing, focus-group setting are developed.
3 | Data collection for Needs Assessment report |  |  |  | All interviews, focus-groups, questionnaries are held, results and data collected.
4 | Development of the first draft of the Needs Assessment report and presentation of the results on National Consultation meeting with participation of CAREC and USAID |  |  |  | Presentation made, comments received
5 | Preparation of the final report on Needs Assessment considering all comments received |  |  |  | The report is done in accordance with the regional methodology and structure, and considering all received comments
TOTAL |  | 0 |  | 0 | GROSS
| Project Coordinator Yekaterina Strikeleva |  |  | Expert